## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2225-swen-261-03-d-name
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As an Owner, I want to have a different version of the site so that I can manage the site. | GIVEN I am an owner WHEN I put in the admin username THEN the system should pull up the owner version of the store and return a status code of 200 (OK) | Pass | TOT; 3/27/23 | Pass | TOT; 4/10/23
| GIVEN I am an owner WHEN I put in a non-admin username THEN the system should say invalid username and return a status code of 404 (NOT_FOUND) | Pass | TOT; 3/27/23 | Pass | TOT; 4/10/23
As a Customer, I want to have a different version of the site so that I can shop in the e-store. | GIVEN I am a customer WHEN I put in my username THEN the system should pull up the customer version of the store that contains the persistent data for me and return a status code of 200 (OK) | Pass | TOT; 3/27/23 | Pass | TOT; 4/10/23
| GIVEN I am a customer WHEN I put in a username different than mine THEN the system should say invalid username and return a status code of 404 (NOT_FOUND) | Pass | TOT; 3/27/23 | Pass | TOT; 4/10/23
As an Owner/Buyer I want to have a username so that I can make sure it's my account. | GIVEN I register an account WHEN I create a username that does not exist THEN the system should create a username with persistent data for me and return a status code of 200 (OK) | Pass | TOT; 3/27/23 | Pass | TOT; 4/10/23
| GIVEN I register an account WHEN I create a username that already exists THEN the system should return a staus code of 409 (CONFLICT) | Pass | TOT; 3/27/23 | Pass | TOT; 4/10/23
As a Buyer I want to search all the products so that I can quickly get to the products that I want. | GIVEN that I enter a sequence of characters into the search bar WHEN there are products that contain the same sequence THEN the system should show those products and return status code 302 (FOUND) | Pass | FSSZ 3/27/2023 | Pass | FSSZ 4/10/23
| GIVEN that I enter a sequence of characters into the search bar WHEN there are products that don't contain the same sequence THEN the system should show no products and return status code 404 (NOT_FOUND) | Pass | FSSZ 3/27/2023 | Pass | FSSZ 4/10/23
As an owner I want to be able to add to the inventory so that customers can keep shopping. | GIVEN I submit a request to add inventory WHEN there is not a product in the inventory with the same given properties THEN the system should add the product to the inventory list, save the inventory list, and return a status code of 200 (OK) | Pass | FSSZ 3/27/2023 | Pass | FSSZ 4/10/23
| GIVEN I submit a request to add inventory WHEN there is a product in the inventory with the same given properties THEN the system should return a status code of 409 (CONFLICT) | Pass | FSSZ 3/27/2023 | Pass | FSSZ 4/10/23
As an owner I want to be able to remove some of the inventory so that the customer won't be able to purchase it. | GIVEN I submit a request to remove a product from the inventory WHEN there is a product with the given properties THEN the system should delete the product from the inventory list and should return a status code of 200 (OK) | Pass | FSSZ 3/27/2023 | Pass | FSSZ 4/10/23
| GIVEN I submit a request to remove a product from the inventory WHEN there is not a product with the given properties THEN the system should return a status code of 404 (NOT_FOUND) | Pass | FSSZ 3/27/2023 | Pass | FSSZ 4/10/23
As an owner I want to be able to modify the inventory so that the buyer can shop for new items or so that they cannot. | GIVEN I submit a request to modify a product in the inventory WHEN there is a product with the given properties THEN the system should modify the given product with the provided edits to the properties and return the updated product and a status code of 200 (OK) | Pass | FSSZ 3/27/2023 | Pass | FSSZ 4/10/23
| GIVEN I submit a request to modify a product in the inventory WHEN there is not a product with the given properties THEN the system should return a status code of 404 (NOT_FOUND) | Pass | FSSZ 3/27/2023 | Pass | FSSZ 4/10/23
As a CUSTOMER I want to add to my shopping cart so that the shopping cart can hold the items I want. | GIVEN there is an available item WHEN I add it to my shopping cart THEN the system should add the same item to my shopping cart and should return status code 200 (OK). | Pass | J.L method passes tests 3/27/23 | Pass | J.L method passes test 04/10/2023
| GIVEN there is not an available item WHEN I add it to my shopping cart then the system should not add the item to my shopping cart and the should return code 404 (NOT_FOUND). | Pass | J.L method passes test 3/27/23 | Pass | J.L method passes test 04/10/2023
As a CUSTOMER I want to be able to remove items from my shopping cart so that I am able to purchase the correct items | GIVEN I have items in my shopping cart WHEN I remove them from the shopping cart THEN the system should remove that item from my shopping cart and return status code 200 (OK). | Pass | J.L method passes test 3/27/23 | Pass | J.L method passes test 04/10/2023
| GIVEN I do not have items in my shopping cart WHEN I remove them from the shopping cart THEN the system should not change the empty shopping cart and return status code 404 (NOT_FOUND). | Pass | J.L method passes test 3/27/23 | Pass | J.L method passes test 04/10/2023
As a Buyer, I want to view all the products so that I can choose what to purchase. | Given when the website is up and running, when the user visits the page, there will be a catalog of products to choose from. | Pass | J.L. method passes test 3/27/23 | Pass | J.L method passes test 04/10/2023
AS a Developer I WANT to submit a request to create a new product (name, price, quantity) SO THAT it is available to in the inventory. | GIVEN I submit a product object WHEN no product with the given name exists THEN the system should create the product, add it to the inventory, save to the persistent store, and return the product object and a status code of 201 (CREATED) | Pass | P.J.E method passes test 2/21/23 | Pass | P.J.E method passes test 4/10/23
| GIVEN I submit a product object WHEN a product with the given name already exists THEN the system should return a status code of 409 (CONFLICT) | Pass | P.J.E method passes test 2/21/23 | Pass | P.J.E method passes test 4/10/23
AS a Developer I WANT to submit a request to get a single product SO THAT I can access the price and quantity. | GIVEN I submit a get request for a product WHEN a product with the given name exists THEN the system should return the product object and a status code of 302 (FOUND) | Pass | P.J.E method passes test 2/21/23 | Pass | P.J.E method passes test 4/10/23
| GIVEN I submit a get request for a product WHEN a product with the given name does not exist THEN the system should return with a status code of 404 (NOT_FOUND) | Pass | P.J.E method passes test 2/21/23 | Pass | P.J.E method passes test 4/10/23
As a Developer I want to submit a request to delete a single product SO THAT it is no longer in the inventory. | GIVEN I submit a request to delete a product WHEN there is a product with the given name THEN the system should delete the product, remove it from the inventory, save to the persistant store, and return a status code of 200 (OK) | Pass | P.J.E method passes test 2/21/23 | Pass | P.J.E method passes test 4/10/23
| GIVEN I submit a request to delete a product WHEN there is not a product with the givne name THEN the system should return a status code of 404 (NOT_FOUND) | Pass | P.J.E method passes test 2/21/23 | Pass | P.J.E method passes test 4/10/23
AS a Developer I WANT to submit a request to get the products in the inventory whose name contains the given text SO THAT I have access to only those products. | GIVEN I submit a search request WHEN there is a/are product(s) with the given search THEN the system should return an array of the product(s) that contain the searched string and a status code of 200 (OK) | Pass | P.J.E method passes test 2/21/23 | Pass | P.J.E method passes test 4/10/23
| GIVEN I submit a search request WHEN there are not any products with the given search THEN the system should return an empty array of products and a status code of 200 (OK) | Pass | P.J.E method passes test 2/21/23 | Pass | P.J.E method passes test 4/10/23
AS a Developer I WANT to submit a request to get the entire inventory SO THAT I have access to all of the products. | GIVEN I submit a request for the inventory WHEN products exist in the inventory THEN the system should return a list of products and a status code of 200 (OK) | Pass | T.T method passes test 2/22/23 | Pass | T.T method passes test 4/10/23
| GIVEN I submit a request for the inventory WHEN no products exist in the inventory THEN the system should return an empty list of products and a status code of 200 (OK) | Pass | T.T method passes test 2/22/23 | Pass | T.T method passes test 4/10/23
AS a Developer I WANT to submit a request to get the entire inventory SO THAT I have access to all products and their details | GIVEN I submit a request for the inventory WHEN products exist in the inventory THEN the system should return a list of products and a status code of 200 (OK) | Pass | P.J.E method passes test 2/21/23 | Pass | P.J.E method passes test 4/10/23
| GIVEN I submit a request for the inventory WHEN no products exist in the inventory THEN the system should return an empty list of products and a status code of 200 (OK) | Pass | P.J.E method passes test 2/21/23 | Pass | P.J.E method passes test 4/10/23
As a Customer, I want to be able to check out my items so that they disappear from my shopping cart to simulate actually checking out. | GIVEN I have items in my shopping cart WHEN I proceed to checkout THEN the system should purchase the items, the inventory for the items bought should be decreased and return a status code of 200 (OK). |  |  | Pass | J.L method passes test 04/10/2023
| GIVEN no items in the shopping cart WHEN I proceed to checkout THEN the system should not purchase the items, the inventory should not change, and return status code 404 (NOT_FOUND). |  |  | Pass | J.L method passes test 04/10/2023
As an Owner, I want to be able to change the discount codes so that I can change how much they give off and what the code is. | GIVEN there is a valid discount code WHEN I change the discount value THEN the system should change the discount amount associated with the code and return status code 200 (OK) |  |  | Pass | J.L method passes test 04/10/2023
As an Owner, I want to be able to verify if a discount code is valid or not. | GIVEN a valid discount code WHEN the discount code is applied THEN the system should discount the price as necessary and return a status code of 200 (OK) |  |  | Pass | FSSZ 4/10/23
| GIVEN an invalid discount code WHEN the discount code is determined invalid THEN the system should not apply the discount and return a status code of 404 (NOT_FOUND) |  |  | Pass | FSSZ 4/10/23
As a customer, I want to be able to sort by color, so that I can narrow down the items shown. | GIVEN I select a color WHEN there are products that have the color selected THEN the system should show those products and return a status code of 200 (OK) |  |  | Pass | FSSZ 4/10/23
| GIVEN I select a color WHEN there are no products that have the color selected THEN the system should show no products and return a status code of 404 (NOT_FOUND) |  |  | Pass | FSSZ 4/10/23
As a customer, I want to be able to filter by sport, so that I can narrow down the items shown. | GIVEN I select a sport WHEN there are products that have the sport selected THEN the system should show those products and return a status code of 200 (OK) |  |  | Pass | FSSZ 4/10/23
| GIVEN I select a color WHEN there are no products that have the sport selected THEN the system should show no products and return a status code of 404 (NOT_FOUND) |  |  | Pass | FSSZ 4/10/23
As a customer, I want to be able to sort by price, to narrow down my search result. | GIVEN I click the price sort button WHEN the sort is set to ascending THEN the system should display the products by price from lowest to highest and return a status code of 200 (OK) |  |  | Pass | FSSZ 4/10/23
| GIVEN I click the price sort button WHEN the sort is set to descending THEN the system should display the products by price from highest to lowest and return a status code of 200 (OK) |  |  | Pass | FSSZ 4/10/23
As a customer, I want to be able to sort by inventory quantity, to narrow down my search result. | GIVEN I click the quantity sort button WHEN the sort is set to ascending THEN the system should display the products by quantity from lowest to highest and return a status code of 200 (OK) |  |  | Pass | FSSZ 4/10/23
| GIVEN I click the quantity sort button WHEN the sort is set to descending THEN the system should display the products by quantity from highest to lowest and return a status code of 200 (OK) |  |  | Pass | FSSZ 4/10/23