## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2225-swen-261-03-d-name
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As an Owner, I want to have a different version of the site so that I can manage the site. | GIVEN I am an owner WHEN I put in the admin username THEN the system should pull up the owner version of the store and return a status code of 200 (OK) | Pass | TOT; 3/27/23
| GIVEN I am an owner WHEN I put in a non-admin username THEN the system should say invalid username and return a status code of 404 (NOT_FOUND) | Pass | TOT; 3/27/23
As a Customer, I want to have a different version of the site so that I can shop in the e-store. | GIVEN I am a customer WHEN I put in my username THEN the system should pull up the customer version of the store that contains the persistent data for me and return a status code of 200 (OK) | Pass | TOT; 3/27/23
| GIVEN I am a customer WHEN I put in a username different than mine THEN the system should say invalid username and return a status code of 404 (NOT_FOUND) | Pass | TOT; 3/27/23
As an Owner/Buyer I want to have a username so that I can make sure it's my account. | GIVEN I register an account WHEN I create a username that does not exist THEN the system should create a username with persistent data for me and return a status code of 200 (OK) | Pass | TOT; 3/27/23
| GIVEN I register an account WHEN I create a username that already exists THEN the system should return a staus code of 409 (CONFLICT) | Pass | TOT; 3/27/23
As a Buyer I want to search all the products so that I can quickly get to the products that I want. | GIVEN that I enter a sequence of characters into the search bar WHEN there are products that contain the same sequence THEN the system should show those products and return status code 302 (FOUND) | Pass | FSSZ 3/27/2023
| GIVEN that I enter a sequence of characters into the search bar WHEN there are products that don't contain the same sequence THEN the system should show no products and return status code 404 (NOT_FOUND) | Pass | FSSZ 3/27/2023
As an owner I want to be able to add to the inventory so that customers can keep shopping. | GIVEN I submit a request to add inventory WHEN there is not a product in the inventory with the same given properties THEN the system should add the product to the inventory list, save the inventory list, and return a status code of 200 (OK) | Pass | FSSZ 3/27/2023
| GIVEN I submit a request to add inventory WHEN there is a product in the inventory with the same given properties THEN the system should return a status code of 409 (CONFLICT) | Pass | FSSZ 3/27/2023
As an owner I want to be able to remove some of the inventory so that the customer won't be able to purchase it. | GIVEN I submit a request to remove a product from the inventory WHEN there is a product with the given properties THEN the system should delete the product from the inventory list and should return a status code of 200 (OK) | Pass | FSSZ 3/27/2023
| GIVEN I submit a request to remove a product from the inventory WHEN there is not a product with the given properties THEN the system should return a status code of 404 (NOT_FOUND) | Pass | FSSZ 3/27/2023
As an owner I want to be able to modify the inventory so that the buyer can shop for new items or so that they cannot. | GIVEN I submit a request to modify a product in the inventory WHEN there is a product with the given properties THEN the system should modify the given product with the provided edits to the properties and return the updated product and a status code of 200 (OK) | Pass | FSSZ 3/27/2023
| GIVEN I submit a request to modify a product in the inventory WHEN there is not a product with the given properties THEN the system should return a status code of 404 (NOT_FOUND) | Pass | FSSZ 3/27/2023
As a CUSTOMER I want to add to my shopping cart so that the shopping cart can hold the items I want. | GIVEN there is an available item WHEN I add it to my shopping cart THEN the system should add the same item to my shopping cart and should return status code 200 (OK). | Pass | J.L method passes tests 3/27/23 | Pass
| GIVEN there is not an available item WHEN I add it to my shopping cart then the system should not add the item to my shopping cart and the should return code 404 (NOT_FOUND). | Pass | J.L method passes test 3/27/23
As a CUSTOMER I want to be able to remove items from my shopping cart so that I am able to purchase the correct items | GIVEN I have items in my shopping cart WHEN I remove them from the shopping cart THEN the system should remove that item from my shopping cart and return status code 200 (OK). | Pass | J.L method passes test 3/27/23 | Pass
| GIVEN I do not have items in my shopping cart WHEN I remove them from the shopping cart THEN the system should not change the empty shopping cart and return status code 404 (NOT_FOUND). | Pass | J.L method passes test 3/27/23